COS80027 Assignment 3

Detailed Task Division Plan - Updated Timeline

Member 1 completed by Ploy | Member 2 deadline: 30 May 2026 night | Rough full version target: 3 June 2026 night | Final submission: 7 June 2026, 23:59

# Summary

I asked the tutor about Assignment 3. The tutor confirmed two important points:

1. Everyone needs to have contribution in both coding and notebook explanation for their own part.

2. The final model comparison section must be included in development_DL.ipynb.

The actual submission deadline is Sunday, 7 June 2026 at 23:59.

Member 1 dataset preprocessing is already completed. Our group should now finish a rough full version by 3 June 2026 night, so we can ask the tutor in class on 4 June if anything is unclear. Then we can use 5-6 June to improve the notebooks, appendix, and presentation before final submission.

Note: No separate full report is required. The only extra written file is appendix.pdf, which is for supplementary figures/results only. Notebook Explanation Contribution means each member writes a short explanation for the section they coded.

# Final Files We Need To Submit

1. development_DL.ipynb

2. development_ML.ipynb

3. appendix.pdf - maximum 3 pages

4. One .zip file named after Ploy's surname (team leader)

Do not include unnecessary files in the final zip.

# Recommended Work Structure

We have 6 members. The work should be divided by member number. Each member must choose one number and complete both:

code contribution

notebook explanation contribution

The tasks depend on each other, so the deadlines are in order. Ploy has completed Member 1 dataset/preprocessing early, so Member 2 and Member 4 can start from the prepared data. Ploy will also prepare the presentation file/template and complete the final overall check, while each member still adds their own notebook and slide content.

# Member 1 (Ploy) - Dataset Preprocessing + Team Leader Final Check

## Main Responsibility

Prepare the CIFAR-10 dataset for both Deep Learning and Machine Learning notebooks. As team leader, Ploy also prepares the presentation file/template, checks the final files, creates the final zip, and submits on Canvas.

## Code Contribution

Member 1 should write code for:

loading the CIFAR-10 dataset

defining the 10 class names

checking the shape of training and testing data

displaying sample images from the dataset

normalizing images for Deep Learning

preparing labels in the correct format

making sure both DL and ML use the same train/test split

## Notebook Explanation Contribution

Member 1 should write a short explanation about:

what CIFAR-10 is

how many images are in the dataset

how many classes there are

what the 10 classes are

what preprocessing was applied

why normalization is needed

why the same train/test split should be used for DL and ML

## Output Needed

Member 1 should provide:

working dataset loading code

sample image plot

class names list

preprocessing explanation

data ready for Member 2, Member 3, Member 4, Member 5, and Member 6

## Deadline

Completed 28 May 2026

Member 1 was completed on 28 May. Member 2 and Member 4 can now start using the prepared CIFAR-10 data and train/test split.

## Ploy / Final Check Responsibility

Member 1 should also:

prepare the presentation file/template and slide structure

assign slide sections so each member adds their own content

check that both notebooks are complete and clean

check that the contribution table is included at the beginning of development_DL.ipynb

check that the final comparison is included in development_DL.ipynb

check that appendix.pdf is included and is maximum 3 pages

create the final zip file and submit on Canvas

Note: Ploy does the final overall check, but each member must still clean/comment their own code section and add their own presentation content.

Leadership deadlines: presentation template by 4 June after class; final overall check by 6 June night; final submission by 7 June 23:59.

# Member 2 - Deep Learning Model

## Main Responsibility

Build and train the Deep Learning model in development_DL.ipynb.

## Code Contribution

Member 2 should write code for:

choosing the Deep Learning framework, such as TensorFlow/Keras or PyTorch

defining the Deep Learning task as supervised multi-class image classification

creating the model architecture

training the model on CIFAR-10

setting training parameters such as:

epochs

batch size

optimizer

learning rate

loss function

saving training history for later plotting

## Recommended Model

Use one of these:

CNN from scratch

MobileNetV2 fine-tuning

ResNet fine-tuning

If using a pre-trained model, it must not be pre-trained on CIFAR-10. ImageNet pre-trained models are normally acceptable, but this should be clearly stated in the notebook.

## Notebook Explanation Contribution

Member 2 should write a short explanation about:

why the chosen architecture is suitable for image classification

what framework was used

what the model layers do

what training parameters were used

whether the model was trained from scratch or fine-tuned

## Output Needed

Member 2 should provide:

trained Deep Learning model

training history

explanation of architecture and training setup

## Deadline

30 May 2026

# Member 3 - Deep Learning Evaluation And Final Comparison

## Main Responsibility

Evaluate the Deep Learning model and add the final DL vs ML comparison into development_DL.ipynb.

## Code Contribution

Member 3 should write code for:

evaluating the DL model on the test set

calculating test accuracy

generating the confusion matrix

plotting training loss across epochs

optionally plotting training accuracy across epochs

showing sample test images with predicted labels and true labels

creating the final comparison table between DL and ML

creating a comparison graph, such as accuracy bar chart

## Notebook Explanation Contribution

Member 3 should write a short explanation about:

DL test accuracy

which classes the DL model predicted well

which classes the DL model confused

whether the model showed signs of overfitting

comparison between DL and ML

advantages and disadvantages of Deep Learning

why DL may perform better for image classification

## Output Needed

Member 3 should provide:

DL accuracy

DL confusion matrix

training loss graph

sample prediction images

final comparison section in development_DL.ipynb

## Deadline

DL evaluation: 1 June 2026

Final comparison draft: 2 June 2026; final update after ML results by 3 June 2026

# Member 4 - Machine Learning Feature Extraction

## Main Responsibility

Extract image features for the Machine Learning model in development_ML.ipynb.

## Code Contribution

Member 4 should write code for:

preparing CIFAR-10 images for feature extraction

converting images if needed, for example RGB to grayscale

extracting image features

creating feature arrays for train and test data

scaling or standardizing features if needed

## Recommended Feature Extraction Methods

Recommended option:

HOG features

Stronger option:

HOG features + colour histogram

Optional comparison:

compare HOG vs colour histogram if there is enough time

## Notebook Explanation Contribution

Member 4 should write a short explanation about:

what feature extraction means

why traditional ML cannot easily use raw image pixels

what HOG features are

why HOG is useful for image classification

what preprocessing was needed before feature extraction

## Output Needed

Member 4 should provide:

extracted training features

extracted testing features

feature extraction explanation

feature arrays ready for Member 5

## Deadline

30 May 2026

# Member 5 - Machine Learning Model And Hyperparameter Tuning

## Main Responsibility

Train the traditional Machine Learning model using the extracted features.

## Code Contribution

Member 5 should write code for:

choosing one Machine Learning algorithm

training the model using extracted features

tuning at least one hyperparameter

using validation split or cross-validation for tuning

selecting the best model

## Recommended ML Model

Recommended option:

SVM

Possible alternatives:

Random Forest

KNN

Recommended hyperparameters to tune:

SVM: C, kernel, gamma

Random Forest: n_estimators, max_depth

KNN: n_neighbors

## Notebook Explanation Contribution

Member 5 should write a short explanation about:

what Machine Learning algorithm was selected

why the algorithm was selected

which hyperparameter was tuned

what values were tested

which value performed best

why test data should not be used for tuning

## Output Needed

Member 5 should provide:

trained ML model

hyperparameter tuning results

best hyperparameter values

explanation of ML model and tuning

## Deadline

1 June 2026

# Member 6 - Machine Learning Evaluation, Appendix Support, And Final Packaging Support

## Main Responsibility

Evaluate the ML model, provide ML results to Member 3, and help prepare appendix/presentation/final submission.

## Code Contribution

Member 6 should write code for:

evaluating the ML model on the test set

calculating ML test accuracy

generating ML confusion matrix

generating classification report

saving or recording ML results clearly

preparing plots or tables for appendix if needed

## Notebook Explanation Contribution

Member 6 should write a short explanation about:

ML test accuracy

ML confusion matrix

which classes the ML model predicted well

which classes the ML model confused

limitations of the ML approach

what ML results should be compared with DL

## Appendix And Presentation Support

Member 6 should also help with:

appendix figures

comparison table formatting

slide preparation

checking that all final outputs are included

checking that file names are correct

## Output Needed

Member 6 should provide:

ML accuracy

ML confusion matrix

classification report

ML results summary for Member 3

appendix/presentation support

## Deadline

ML evaluation: 3 June 2026

Appendix/slides draft: 4-5 June 2026

# Dependency Order

The tasks should be completed in this order because later tasks need outputs from earlier tasks:

1. Member 1 has completed dataset preprocessing first.

2. Member 2 starts the DL model after the dataset is usable.

3. Member 4 starts ML feature extraction after the dataset is usable.

4. Member 3 evaluates the DL model after Member 2 has trained it.

5. Member 5 trains and tunes the ML model after Member 4 has extracted features.

6. Member 6 evaluates the ML model after Member 5 has trained/tuned it.

7. Member 3 and Member 6 complete the final DL vs ML comparison after both DL and ML results are ready.

8. Everyone helps clean notebooks, write contribution explanations, prepare appendix, and prepare presentation.

# Overall Timeline

| Task | Member | Deadline | Reason |
| --- | --- | --- | --- |
| Choose roles | Everyone | 28 May | Everyone needs a clear role before coding starts |
| Dataset preprocessing | Ploy / Member 1 | 28 May | Completed first; DL and ML now use the same prepared dataset split |
| DL model | Member 2 | 30 May | Can now start because Member 1 data is ready |
| ML feature extraction | Member 4 | 30 May | Can now start because Member 1 data is ready |
| DL evaluation | Member 3 | 1 June | Needs trained DL model from Member 2 |
| ML model and tuning | Member 5 | 1 June | Needs extracted features from Member 4 |
| ML evaluation | Member 6 | 3 June | Needs trained/tuned ML model from Member 5 |
| Final comparison | Member 3 and Member 6 | 3 June | Member 3 can draft by 2 June; final update needs Member 6 ML results |
| Rough full version | Everyone | 3 June | Needed so we can ask tutor questions on 4 June |
| Notebook final check | Everyone | 5 June | Check notebooks after tutor feedback |
| Appendix and presentation slides final draft | Member 6 + all members, checked by Ploy | 4-5 June | Ploy prepares slide file/template; each member adds their own content |
| Fix and improve | Everyone | 6 June night | Use feedback and final checks to improve final work |
| Final submission | Ploy / Member 1 | 7 June 23:59 | Submit final zip file |

# Notebook Structure

# development_DL.ipynb

This notebook should include:

1. Team member names and contribution table

2. Problem statement

3. Dataset description

4. Dataset preprocessing

5. Deep Learning task formulation

6. Framework and architecture selection

7. Model development and training

8. Deep Learning performance assessment

9. Training loss plot

10. Accuracy and confusion matrix

11. Sample predictions

12. Final model comparison between DL and ML

# development_ML.ipynb

This notebook should include:

1. Problem statement

2. Dataset loading and preprocessing

3. Machine Learning task formulation

4. Feature extraction method

5. ML model selection

6. Hyperparameter tuning

7. ML model training

8. ML performance assessment

9. Accuracy and confusion matrix

10. Classification report

11. Final ML results summary for the DL notebook comparison

# appendix.pdf

The appendix should be maximum 3 pages.

It can include:

large confusion matrix figures

training curves

sample predictions

comparison table

hyperparameter tuning results

extra plots that are too large for the notebooks

The appendix should not repeat the notebooks. It should only contain supplementary materials.

# Contribution Table Template

This should be placed near the beginning of development_DL.ipynb.

| Member | Main Role | Code Contribution | Notebook Explanation Contribution | Contribution Factor |
| --- | --- | --- | --- | --- |
| Ploy | Dataset preprocessing + final review | Loaded CIFAR-10, normalized data, displayed samples | Dataset explanation and final checklist | 1.0 |
| Name 2 | DL model | Built and trained CNN/ResNet/MobileNet | DL architecture and training explanation | 1.0 |
| Name 3 | DL evaluation and comparison | DL accuracy, confusion matrix, loss graph, final comparison | DL results and DL vs ML discussion | 1.0 |
| Name 4 | ML feature extraction | Extracted HOG/colour histogram features | Feature extraction explanation | 1.0 |
| Name 5 | ML model and tuning | Trained SVM/Random Forest/KNN and tuned hyperparameters | ML model and tuning explanation | 1.0 |
| Name 6 | ML evaluation and appendix support | ML accuracy, confusion matrix, classification report | ML results, limitations, appendix/presentation support | 1.0 |

# What Each Member Should Write In Their Section

Each member should write:

1. What they did

2. Why they did it

3. Which method/model/parameter was used

4. What result they got

5. Any limitation or issue

The writing does not need to be very long, but it must be clear and connected to their code.

# Important Rules

Ploy prepares the presentation template; each member adds their own slide content.

No separate full report is required; appendix.pdf is only for supplementary materials.

Everyone must contribute code.

Everyone must write a short notebook explanation for their own contribution.

Comments should be added to important code cells.

The final comparison must be in development_DL.ipynb.

Both DL and ML should use the same train/test split.

Do not tune hyperparameters using the test set.

Use the test set only for final evaluation.

Notebooks should be clean before submission.

Remove unnecessary failed code or repeated cells.

Make sure all plots and outputs are visible.

Make sure the final zip contains only the required files.

# Suggested Group Message

Hi everyone, I asked the tutor today about Assignment 3.

The tutor said everyone needs to have contribution in both coding and notebook explanation for their own part. Also, the final model comparison section must be included in development_DL.ipynb.

The actual submission is due on 7 June, but we should finish a rough full version by 3 June night because we have class on 4 June and can ask the tutor if anything is unclear. Then we can use 5-6 June to fix and improve before final submission and prepare the presentation.

I divided the work into 6 member roles. Member 1 is already completed by Ploy, so please choose which remaining member number you want to do:

Member 1 (Ploy): Dataset preprocessing completed 28 May + presentation template + final overall check

Member 2: Deep Learning model - deadline 30 May night

Member 3: Deep Learning evaluation and final comparison - DL evaluation by 1 June, comparison draft by 2 June, final update after ML results by 3 June

Member 4: ML feature extraction - deadline 30 May

Member 5: ML model and hyperparameter tuning - deadline 1 June

Member 6: ML evaluation, appendix support - ML evaluation by 3 June, appendix by 4-5 June

Please reply with the member number you want to do.